## Summary
Open Continuity Protocol 0.3 — Issue Register | Open Continuity Protocol 0.3 — Issue Register | Open Continuity Protocol 0.3 — Issue Register | Open Continuity Protocol 0.3 — Issue Register | Open Continuity Protocol 0.3 — Issue Register | Open Continuity Protocol 0.3 — Issue Register | Open Continuity Protocol 0.3 — Issue Register | Open Continuity Protocol 0.3 — Issue Register | Open Continuity Protocol 0.3 — Issue Register | Open Continuity Protocol 0.3 — Issue Register | Open Continuity Protocol 0.3 — Issue Register | Open Continuity Protocol 0.3 — Issue Register | Open Continuity Protocol 0.3 — Issue Register | Open Continuity Protocol 0.3 — Issue Register
Consolidated Editor's Working Draft · source review issues re-evaluated for OCP 0.3 · 12 August 2026
Register overview | Count |  | Priority | Count
Total inherited issues | 57 |  | P0 | 10
Applied: Yes | 22 |  | P1 | 31
Applied: Partly | 27 |  | P2 | 13
Deferred | 8 |  | P3 | 3
Current evidence context | Value
Working-draft status | Project-authoritative consolidated editor's working draft
Implementation passes | 0
Implementation failures | 0
Reference issue source | OCP v0.1 independent review
Evidence boundary | Applied means reflected in the revised design at the indicated level; it does not establish deployed effectiveness.
Source metadata
Register | OCP 0.3 inherited independent-review issue register
Source review | OCP v0.1 independent review
Incorporated into | OCP 0.2 review draft and re-evaluated for OCP 0.3
Source file | review/issue-register.json

## Issue Register
OCP 0.3 — Inherited Independent-Review Issue Register | OCP 0.3 — Inherited Independent-Review Issue Register | OCP 0.3 — Inherited Independent-Review Issue Register | OCP 0.3 — Inherited Independent-Review Issue Register | OCP 0.3 — Inherited Independent-Review Issue Register | OCP 0.3 — Inherited Independent-Review Issue Register | OCP 0.3 — Inherited Independent-Review Issue Register | OCP 0.3 — Inherited Independent-Review Issue Register
OCP 0.2 review draft and re-evaluated for OCP 0.3
Applied means reflected in the revised design at the indicated level; it does not establish deployed effectiveness.
ID | Priority | Section | Category | Finding | Why it matters | Recommendation | Applied to revised draft?
OCP-P0-001 | P0 | 3, 6, 10, 12 | Authorization boundary | context_grant resembles an authorization artifact but is not bound to an enforceable decision and could be mistaken for a bearer credential. | A request or portable receipt could be accepted as authority, enabling confused-deputy access. | Keep requests inert; use OAuth, GNAP, or a local broker; define grant_receipt as non-secret and non-authorizing; authorize every operation at use time. | Yes
OCP-P0-002 | P0 | 6, 10, 11 | Package binding | The request, authorization decision, credential, client instance, receipt, and package are not cryptographically or transactionally bound. | Substitution, widening, replay, wrong-audience use, and authorization races remain possible. | Bind the exact request and decision revision, effective-authorization hash, issuer/resource, recipient key, purpose, time, and content manifest. | Partly
OCP-P0-003 | P0 | 2, 4, 10 | Authority model | A singular subject and broad steward role cannot express competing rights or establish authority over disclosed data. | One party could approve another person's or an organization's information without a valid basis. | Limit the baseline to competent-adult self-authorization; model aboutness, custody, authority basis, scope, and threshold separately; defer complex cases. | Partly
OCP-P0-004 | P0 | 9, 10, 11 | Import security | Prompt injection, poisoning, archive/parser, SSRF, secret, and active-content controls are descriptive rather than testable requirements. | Imported content can control privileged models or tools, leak secrets, corrupt context, or compromise hosts. | Define trust zones, no-network sandboxing, quantitative limits, persistent taint, inert rendering, secret quarantine, and hostile fixtures. | Yes
OCP-P0-005 | P0 | 14 | Conformance honesty | The L1-L3 ladder mixes locally testable behavior with unobservable downstream purpose, retention, training, and deletion conduct. | A conformance mark could imply privacy or behavioral guarantees that protocol tests cannot prove. | Split structural, semantic, authorization, import-safety, UX, transfer, binding, and external-assurance claims; label evidence as enforced, declared, attested, or audited. | Yes
OCP-P0-006 | P0 | 4.3, Appendix A | Schema architecture | The draft requires one common top-level envelope, but most normative examples omit its required fields. | Independent implementations will choose incompatible shapes and omit security-significant metadata. | Define record, transaction, and manifest envelope families with type-specific required fields; validate every normative example in CI. | Yes
OCP-P0-007 | P0 | Appendix A.2 | Semantic invariant | The stated grant_scope >= package_scope prohibition appears reversed and does not define comparison across authorization dimensions. | Literal implementation could forbid safe narrowing while allowing unsafe widening. | Require package_authorization to be a typed subset of effective_authorization; reject unknown or incomparable constraints; publish property-based negative tests. | Yes
OCP-P0-008 | P0 | 12.4 | Standards overlap | The draft understates Portable AI Memory v1.0, which already covers memory lifecycle, provenance, grants, signatures, export, and mappings. | OCP risks duplicating its closest adjacent format and weakening its standards credibility. | Publish a bidirectional field-level, loss-aware PAM mapping and prefer an OCP governance/presentation profile unless demonstrated gaps require a separate schema. | Partly
OCP-P0-009 | P0 | 2, 4.11, 10.7-10.8 | Third-party and organizational data | The core claims household, relationship, team, organization, and work support without enforceable authority or exfiltration controls. | OCP could normalize private communications and trade secrets into a highly useful disclosure package. | Exclude raw third-party and managed organizational content from the Core Personal Profile and require separately reviewed profiles. | Yes
OCP-P0-010 | P0 | 2, 17, 18 | Vulnerable and joint subjects | Child, guardian, assisted-decision, incapacity, deceased-person, household, and joint cases remain unresolved while the role model appears to permit them. | Implementations may advertise support without adequate rights, transition, disagreement, or withdrawal semantics. | Mark these cases unsupported in core and require profile-specific legal, rights, safety, accessibility, threshold, and withdrawal review. | Deferred
OCP-P1-001 | P1 | 4, 5 | Epistemic terminology | Canonical context can imply complete identity, objective truth, or a single authoritative winner. | The term encourages dossier thinking and overstates what human or provider acceptance establishes. | Use accepted portable context for governance state and reserve canonical only for deterministic representation or bytes. | Yes
OCP-P1-002 | P1 | 4.4 | Object model | Seventeen domain objects are presented as core without complete schemas or interoperability evidence. | A large speculative core slows adoption and produces incompatible lifecycle and security semantics. | Merge claim, goal, decision, instruction, and note into context_item; move conversations, artifacts, credentials, relationships, learning, and lineage into profiles. | Yes
OCP-P1-003 | P1 | 4.5, 5 | Typed values | predicate plus unconstrained value cannot reliably encode datatype, language, unit, reference, structured value, qualifiers, or profile semantics. | Round trips and comparisons lose meaning, while free-form strings become a hidden ontology. | Use URI predicates, typed values, qualifiers, profile schemas, and opaque preservation with explicit loss for unsupported semantics. | Yes
OCP-P1-004 | P1 | 5.3, 12.6 | Provenance | The provenance array accepts arbitrary objects and its PROV mapping is illustrative only. | Implementations cannot consistently distinguish source, activity, actor, time, transformation, and verification. | Define typed source_record and provenance fields; publish a normative PROV mapping and reference C2PA rather than duplicating it. | Partly
OCP-P1-005 | P1 | 4.3, 10.2 | Identifiers and privacy | Global URI requirements conflict with pairwise privacy, and examples disclose stable store and subject identifiers. | Stable identifiers make cross-client correlation and graph joining a built-in capability. | Separate internal IDs, issuer-scoped principals, audience-pairwise subject aliases, and package-local entry IDs; define rotation and merge mappings. | Partly
OCP-P1-006 | P1 | Examples, Appendix A | Example validity | Examples contain 24 invalid label-like UUID URNs, five unregistered OCP URNs, an undefined ocp+blob scheme, and two fake SHA-256 values. | Examples are copied into implementations and contradict claims that the draft is buildable. | Use valid synthetic UUID URNs, specified HTTPS or registered identifiers, computed digests, and automated validation of every example. | Yes
OCP-P1-007 | P1 | 5, 7, 9 | Lifecycle model | Review status, record state, temporal validity, disclosure eligibility, transfer, withdrawal, revocation, and deletion are blended or listed without complete state machines. | Illegal resurrection, stale use, contradictory histories, and unsafe retries become implementation-defined. | Define orthogonal state dimensions, legal transitions, terminal states, immutable decisions/events, and fail-closed transition errors. | Yes
OCP-P1-008 | P1 | 5.7, 7, 11.4 | Concurrency and idempotency | Revision, ETag, stale-write, causal-link, and payload-bound idempotency rules are incomplete. | Concurrent reviewers or providers can overwrite authority decisions or duplicate side effects. | Require monotonic revision, expected revision or If-Match, immutable events, payload-bound idempotency keys, and no last-write-wins for authority. | Partly
OCP-P1-009 | P1 | 6 | Request-receipt-package comparison | The three objects differ conceptually but lack a complete containment algorithm and binding chain across all authorization dimensions. | A decision can widen a request or a package can exceed the effective decision in an incomparable dimension. | Define typed comparators for selectors, views, purpose, audience, time, processing, retention, offline use, proposal rights, and delegation; unknown comparison denies. | Partly
OCP-P1-010 | P1 | 6.8, 10, consent | Client declarations | Retention, training, processors, logging, derivatives, deletion, and forwarding are unauthenticated requester strings. | The most important privacy terms can change after approval and remain only unverified promises. | Require a signed, versioned, expiring client_declaration; bind its digest into request, receipt, and package; label assurance honestly. | Partly
OCP-P1-011 | P1 | 6.9, 12 | Delegation | A delegation string has no child decision, actor chain, attenuation proof, depth limit, or new audience-specific package. | Agents can broaden access, forward context, or obscure the true processor. | Default delegation depth to zero; require established token exchange, strict intersection, a child decision, actor chain, and new recipient encryption per hop. | Deferred
OCP-P1-012 | P1 | 6.4, 11.7 | Package kinds | Runtime disclosure and offline export or transfer packages share ambiguous language and security assumptions. | A long-lived archive may be treated as current runtime context or as authorization. | Define distinct runtime, transfer, and offline package types; transfer enters quarantine and carries no runtime or action authority. | Yes
OCP-P1-013 | P1 | 10.9-10.10 | Cryptographic package protection | TLS, JCS, and a digest do not specify issuer authentication, recipient confidentiality, signed coverage, key trust, rotation, or algorithms. | A digest can detect change but not who issued a package, and plaintext remains forwardable. | Select reviewed signature and recipient-encryption profiles; define signed view, attachment coverage, key lifecycle, algorithm agility, and interoperable vectors. | Partly
OCP-P1-014 | P1 | 10.12 | Local-first security | A loopback service is suggested without app identity, pairing, CSRF/CORS, Host/origin, DNS-rebinding, socket, keychain, or backup rules. | Any local process or hostile browser origin may reach highly sensitive context. | Prefer an OS broker or Unix socket; otherwise require secure pairing, instance keys, strict Host/origin checks, no ambient cookies, CSRF defense, and protected storage. | Partly
OCP-P1-015 | P1 | 9, 10 | Parser and content safety | Archive size, path, MIME, recursion, URL fetch, redirect, active content, decoder, and secret-detection limits are absent. | Imports enable denial of service, path traversal, SSRF, malware, parser exploitation, and credential leakage. | Publish quantitative limits and hostile fixtures; parse in a sandbox with no network or ambient credentials; reject traversal, bombs, and active content. | Partly
OCP-P1-016 | P1 | 13.3 | Extensions | Unknown non-critical extensions may be preserved or ignored without prohibiting their runtime disclosure, rendering, indexing, or model processing. | Extensions become covert channels around minimization and review rules. | Permit opaque preservation at rest, but prohibit interpretation, rendering, indexing, model use, and disclosure until understood and explicitly granted. | Yes
OCP-P1-017 | P1 | 8 | Artifact scope | Artifacts are core objects despite unresolved storage, active-format, rights, chunking, authenticity, decoder, and preservation semantics. | The core expands into backup and media infrastructure with severe parser and rights obligations. | Keep artifact references and preservation state in presentations; move bytes, lineage, storage, chunking, C2PA, and active media to a reviewed profile. | Yes
OCP-P1-018 | P1 | 10.7 | Third-party privacy | Third-party content is excluded only by a SHOULD, while pseudonymization is treated as broadly sufficient. | Relationship graphs, presence, and source detail remain re-identifiable and can expose another person. | Prohibit raw third-party content in the Core Personal Profile and protect relationship edges, source details, and omission metadata. | Yes
OCP-P1-019 | P1 | 10.8 | Organizational DLP | Custody, source environment, confidentiality, exportability, and organizational policy are optional advisory fields. | A personal context store can become a structured corporate data-loss channel. | Require these controls in an organizational profile and quarantine managed-source content from personal core absent explicit policy authorization. | Deferred
OCP-P1-020 | P1 | 3, 6, 10 | Consent and HCI | A human-readable purpose is required, but client identity, processors, material changes, anti-dark-pattern behavior, accessibility, and high-risk confirmation are not. | A technically valid access decision may still be unintelligible, deceptive, inaccessible, or coerced. | Require provider-controlled UI, default deny, separate choices, equivalent decline, material-change re-consent, WCAG 2.2 AA, and comprehension testing. | Partly
OCP-P1-021 | P1 | 9.7-9.8 | Deletion evidence | Erasure records omit derivative scope, processors, backups, legal holds, exceptions, verification method, and verifier independence. | A reported-complete status can still create a misleading impression of universal deletion. | Define scoped deletion status records and separate external verification attestations; generate exact qualified UI language and preserve residual-copy warnings. | Partly
OCP-P1-022 | P1 | 11 | HTTP binding | The endpoint list lacks complete schemas, authorization behavior, status codes, ETags, idempotency scope, pagination, caching, retry, rate limits, and audit events. | Independent clients cannot interoperate safely from path names and prose alone. | Publish a complete OpenAPI binding or keep HTTP non-normative; reuse RFC 9457 problems and RFC 9728 protected-resource metadata. | Partly
OCP-P1-023 | P1 | 12 | Standards mappings | Adjacent standards are named, but mappings are mostly prose rather than versioned, testable profiles. | Implementations can claim the same compatibility while serializing different semantics or duplicating existing protocols. | Publish mappings and fixtures for PAM, OAuth/RAR/PRM, MCP, A2A, PROV, C2PA, VC, DPV, Solid, CloudEvents, and OpenTelemetry. | Deferred
OCP-P1-024 | P1 | 9.6, 14.5 | Round-trip conformance | Round-trip SHOULD language lacks semantic-equivalence rules, exception manifests, unknown-field behavior, and two-provider evidence. | Portability can silently discard meaning while still being reported as successful. | Define semantic equivalence and explicit loss reports; require independently implemented producer-consumer and provider round trips before stable interoperability claims. | Partly
OCP-P1-025 | P1 | 16 | Governance | Neutrality is aspirational; IP terms, contribution rules, registries, appeals, trademarks, conformance marks, and security disclosure remain unsettled. | A commercial sponsor can appear to control a nominally open standard and its conformance oracle. | Adopt public governance and royalty-free IP commitments before stable registries or marks; keep KnowOnce informative and non-privileged. | Partly
OCP-P1-026 | P1 | Scope, GDPR, EU Data Act | Legal-claim boundary | Portability language could be read as establishing a legal right over provider inference or third-party and organizational data. | Applicable rights and legal bases are qualified facts that protocol fields cannot establish. | State that OCP may support voluntary portability and governance workflows; never equate protocol conformance with legal compliance; require deployment-specific legal review. | Yes
OCP-P1-027 | P1 | 1.4, 4.4, 6.4, 10 | External action authority | Descriptive action, decision, instruction, and credential content can look like current authority to an agent even though context access is not action permission. | A model may treat historical approval or injected prose as permission to send, buy, delete, or invoke tools. | Require external_action_authority to be none in core packages; treat instructions as untrusted data; require separate fresh domain authorization for concrete actions. | Yes
OCP-P1-028 | P1 | 2, 6, 11.2 | Client and discovery trust | Provider and client identities are names or URLs without required publisher, client-instance key, authorization-server, resource, or discovery trust bindings. | Provider impersonation, client phishing, authorization-server mix-up, and unsafe discovery become straightforward. | Bind issuer, resource, authorization server, client ID, client-instance key, publisher declaration, and trust method; require exact matching and SSRF-safe discovery. | Partly
OCP-P1-029 | P1 | 11.3 | Item retrieval authorization | Direct item retrieval is protected only in prose while stable item identifiers and package references may be enumerable. | Broken object-level authorization can bypass package minimization, field views, expiry, and revocation. | Authorize every item read against the active credential, receipt, client instance, audience, purpose, selector, and field view; disclose only opaque package-local aliases. | Partly
OCP-P1-030 | P1 | 7 | Proposal abuse | Proposal rights lack normative rate limits, spam handling, trusted rendering, batch-review limits, and malicious-client quarantine. | Proposal fatigue and deceptive content can turn nominal human review into silent or coerced acceptance. | Rate-limit by client and data class, render in provider-controlled UI, prohibit risky bulk acceptance, bind expected revisions, and retain reversible quarantine. | Yes
OCP-P1-031 | P1 | 4.4, 10 | Credentials and capabilities | Credential objects sit near the core without a hard prohibition on raw secrets or a distinction between evidence, references, presentations, and activated capabilities. | Tokens, keys, cookies, and recovery codes can leak into packages, logs, models, or action paths. | Exclude credential and capability transport from core; prohibit raw secrets; require a separately reviewed reference or presentation profile if a use case is proven. | Deferred
OCP-P2-001 | P2 | 6.2-6.8 | Purpose and scope vocabulary | Free-form or locally named purposes and scopes cannot be ordered safely across providers. | String-prefix matching or semantic guessing can widen access. | Use URI identifiers, versioned registries or profiles, human descriptions, and fail-closed comparison; publish DPV mapping experiments. | Partly
OCP-P2-002 | P2 | 5.5 | Time semantics | Created, observed, acquired, valid, confirmed, review, expiry, supersession, withdrawal, and deletion times are not consistently separated. | Stale or historically scoped context may appear current, and implementations will disagree on precedence and clock behavior. | Separate record time from source time; define precedence, skew, historical mode, review-due behavior, and hard valid-until exclusion. | Partly
OCP-P2-003 | P2 | 10.6 | Sensitivity model | One ordinal sensitivity scale cannot represent health, child, intimate, credential, location, work-confidential, or legal constraints. | Distinct risks collapse into one label, and metadata, summaries, embeddings, and derived features may be underprotected. | Combine a baseline handling class with orthogonal category, profile, and policy references; apply controls to content and derivatives. | Partly
OCP-P2-004 | P2 | 6.4, 10.11 | Omission and audit privacy | Omission lists and audit category names may disclose that sensitive spaces, relationships, or content classes exist. | Transparency metadata can itself become a compact surveillance dossier. | Coarsen or suppress unauthorized omission metadata; minimize, encrypt, segregate, access-control, and narrowly retain audit records. | Partly
OCP-P2-005 | P2 | 11.6 | Events and telemetry | Events and OpenTelemetry are suggested without payload minimization, uniqueness, ordering, retention, duplicate handling, or prohibited fields. | Context can leak through observability, and consumers may mistake events for state, audit, consent, or provenance. | Use reference-and-digest-first CloudEvents and low-cardinality telemetry; prohibit raw context and tokens; define duplicate, reorder, and retention behavior. | Deferred
OCP-P2-006 | P2 | 11, 15 | Developer experience | The draft lacks a complete OpenAPI contract, media-type plan, capability negotiation, validator UX, CLI, and compatibility matrix. | Developers must reverse-engineer prose and examples, producing incompatible behavior and unsafe error handling. | Ship generated documentation, JSON-Pointer validation errors, OpenAPI, validators, fixtures, media/profile negotiation examples, and a tested compatibility matrix. | Partly
OCP-P2-007 | P2 | 17-18 | Future readiness | Speculative agent, household, credential, live-sync, embedding, and rich-media features appear too close to the security-critical core. | Forecasts can destabilize early wire semantics before a use case or two implementers exist. | Keep narrow extension points and threat notes, but defer features until an interoperability need and independent implementers are demonstrated. | Yes
OCP-P2-008 | P2 | Appendix C | Provider observations | Provider-export observations are time-sensitive and are not paired with reproducible public synthetic mapping fixtures. | Readers may treat a snapshot as a current vendor guarantee or sufficient evidence of a standards gap. | Date and version observations, state limits, convert lessons into synthetic fixtures, and never publish uncontrolled personal exports. | Partly
OCP-P2-009 | P2 | Appendix A, 14 | JSON Schema portability | Schema compilation alone does not ensure UUID, URI, timestamp, strict-required, unknown-property, or duplicate-member behavior is consistent across validators. | The same object can pass one implementation and fail or be interpreted differently in another. | Pin JSON Schema 2020-12 vocabularies, require format assertion where relied upon, close core shapes, define I-JSON processing, and run cross-language validator CI. | Partly
OCP-P2-010 | P2 | 11.5 | Error model | The custom error example lacks a complete registered type taxonomy, status mapping, retry semantics, privacy rules, and machine-readable field pointers. | Clients cannot distinguish validation, authorization, conflict, expiry, rate-limit, and transient failures safely. | Use RFC 9457 application/problem+json with stable type URIs, JSON Pointers, request IDs, retry metadata, and privacy-preserving details. | Yes
OCP-P2-011 | P2 | 10.9-10.10 | Key recovery and compromise | Key rotation, compromise, recovery assurance, backup encryption, and re-key behavior are suggestions rather than a coherent lifecycle. | Local-first data may become unrecoverable, while weak recovery can become account takeover or package forgery. | Define key status and rotation events, compromise response, recovery assurance metadata, protected backups, revocation, and export/re-key tests. | Deferred
OCP-P2-012 | P2 | 7, 9, 11 | Availability and abuse limits | Package building, import graphs, proposals, event streams, recursive references, and audit storage lack consistent quotas and backpressure. | Attackers can exhaust CPU, storage, network, audit capacity, or human review attention. | Require pagination, bounded traversal, quantitative quotas, backpressure, per-client rate limits, safe retry, and privacy-preserving limit errors. | Partly
OCP-P2-013 | P2 | 5.3, 9, 14 | Malicious provider detectability | Export, provenance, and audit rules cannot prove that a compromised provider did not alter, omit, or suppress context. | The context provider remains a powerful trust anchor even when packages validate structurally. | Use signed append-only receipts, export exception manifests, and independent verifier tooling; state that these improve detection but cannot prove uncommitted omissions absent transparency infrastructure. | Deferred
OCP-P3-001 | P3 | Throughout | Terminology consistency | Provider, source, subject, steward, user, claim, assertion, event, action, preservation, transfer, deletion, and verification are overloaded. | Normative prose changes meaning across lifecycle, security, identity, and adjacent-standard layers. | Adopt one role and object glossary; prohibit aliases in normative sections and qualify preservation, verification, consent, and deletion claims. | Yes
OCP-P3-002 | P3 | Throughout | Normative language | Some MUST and SHOULD statements are aspirational, lack an actor or condition, omit failure behavior, or describe off-protocol conduct. | Requirements cannot be implemented or tested consistently under BCP 14. | Give every normative rule an actor, condition, action, failure result, assurance boundary, and test ID; move aspirations into informative rationale. | Partly
OCP-P3-003 | P3 | Document structure | Editorial organization | Security rules, open issues, mappings, schemas, examples, and future claims are dispersed, and the source has an unintended near-blank page 35. | Readers miss mandatory behavior and the document appears less mature than its strongest design ideas. | Reorganize by concept, normative rule, schema, edge case, and test; move examples next to rules and complete render QA before publication. | Yes